SemiCon-AI Hackathon

4-Member Weekly Task Plan

Schedule: 30 July - 16 August 2026   |   Round 1 Deadline: 16 August 2026

Rule: Every member rotates through every role across the two weeks.

# Roles Defined

| Role | Responsibility |
| --- | --- |
| ML Engineer | Core code: degradation pipeline, training, inference, configs, CI |
| Data / Validation | Dataset pipeline, validation, experiment logging, metrics, CSV |
| Testing / QA | Unit tests (pytest), CI gates, lint, reproducibility checks |
| Docs / Integration | Technical docs, visual previews, benchmark tables, report, demo |

# Task Dependency Map (Read Before Starting Any Task)

These are hard dependencies. A downstream task cannot start until its upstream task is complete.

- make_dummy_dataset.py

  - wafer_dataset.py (SEMPairDataset)

    - validate_dataset.py → validation_report.json

    - degradation.py → YAML configs → preview_pairs.py

    - train.py

      - Unit tests for train.py

      - Denoising checkpoints (light, medium, heavy)

        - PSNR / SSIM metrics → experiment.csv

        - SR x2 training → SR x2 checkpoint

      - infer.py (requires all checkpoints ready)

        - Unit tests for infer.py

        - Visual before/after gallery

        - Consolidated benchmark table

        - Demo video → Technical report → SUBMISSION

Critical blocking rules

- train.py cannot be fully tested until wafer_dataset.py is working (done by Member 2 in Week 1)

- infer.py depends on at least one trained checkpoint existing

- Benchmark table depends on ALL training runs completed (denoise x3 + SR x2)

- Demo video can only be recorded after infer.py runs successfully on unseen images

- Technical report can only be finalised after the benchmark table is complete

# Daily Integration Protocol (Every Single Day, No Exceptions)

Every evening before ending work, all members must:

- git pull origin main

- Resolve any merge conflicts immediately (do not leave overnight)

- Run: pytest (all tests must pass)

- Run the full pipeline end-to-end (make_dummy_dataset → validate → train stub → infer stub)

- If any step fails, fix it before logging off

- git push your branch and open / update the PR

Why: If everyone works independently for a full week, integration near the deadline becomes a crisis. Catching it daily keeps the risk near zero.

# Definition of Done (DoD)

Every task is only “Done” when ALL of the following are true. Ownership of the task is not enough - the DoD must be met.

### degradation.py

- Implements Gaussian noise, Poisson noise, Gaussian blur, motion blur, SR downsampling (x2, x4)

- Same seed produces bit-identical degraded output (reproducibility test passes)

- All functions have docstrings

- Passes all relevant pytest tests with 0 failures

### wafer_dataset.py (SEMPairDataset)

- Returns (degraded, clean) tensor pairs for all presets

- Crop, augment, degrade pipeline runs without error

- Compatible with PyTorch DataLoader and seed_worker

- Passes dataset unit tests

### make_dummy_dataset.py

- Generates valid placeholder PNGs

- Generates manifest.json with correct schema

- Runs with a single command

### validate_dataset.py

- Detects corrupt files, exits code 1 in CI

- Detects duplicates, exits code 1 in CI

- Produces validation_report.json (schema-versioned) with zero errors on clean data

### ExperimentLogger (logger.py)

- Appends one complete row per run to experiment.csv

- Row includes: config name, git commit hash, epoch, loss, PSNR, SSIM

- git_commit column is never empty

### train.py

- Accepts --config flag and loads any preset YAML

- Trains to convergence with no NaN or Inf loss

- Saves best checkpoint per preset with config snapshot alongside

- Supports resume from checkpoint

- Logs all metrics to experiment.csv via ExperimentLogger

- Passes all unit tests (including seed_worker usage)

### infer.py

- Supports single-image mode and batch mode

- Runs on unseen wafer images without errors

- Outputs are visually inspected and look correct

- Passes all unit tests

### preview_pairs.py

- Produces degradation_preview.png (visual grid)

- Produces *_meta.json per sample

- Preview visually reviewed and approved by team

### Benchmark Table

- Contains all 4 rows: denoise_light, denoise_medium, denoise_heavy, SR x2

- Shows PSNR and SSIM for each

- Results are reproducible via git commit hash

### Demo Video

- Shows: raw wafer image → denoised output → SR x2 output

- Recorded by 14 August (1 day contingency)

- Reviewed and approved by at least one other member

### Technical Report (PDF or DOCX)

- Covers: methodology, results (benchmark table), limitations (x4 / LPIPS / colour deferred)

- All benchmark numbers match experiment.csv

- Proofread by at least one other member

### Test Suite

- 50+ unit tests, 100% pass rate

- CI blocks PRs on lint (ruff/flake8) failures

- CI blocks PRs on test failures

- CI is green on main branch

# Pull Request (PR) Ownership Flow

Every piece of code follows this flow before merging to main:

- Author writes code and tests

- Opens PR with description and DoD checklist ticked

- QA member reviews: runs pytest, checks CI passes

- Docs member checks: confirms docstrings and usage examples

- Merge to main

PR rules

- No self-merges. The author cannot merge their own PR.

- PRs must be opened before end of day, not the morning of the deadline.

- PR description must list which DoD items are satisfied.

- If CI is red, the PR is blocked; the author fixes it before requesting review.

# Bug Ownership Rules

| Bug Severity | Definition | Response |
| --- | --- | --- |
| Critical | Blocks the pipeline (CI broken, training crashes, data corrupt) | Everyone pauses current work and fixes together. Owner leads the fix. |
| Major | Breaks a specific feature but pipeline still runs | Owner fixes within the same day |
| Minor | Cosmetic, non-blocking (typo, wrong log message) | Owner fixes in next available slot, not urgent |

Triage rule: If a bug is found, the person who finds it labels it (Critical / Major / Minor) and posts it in the team channel immediately. Never leave a bug undiscussed overnight.

# Week 1 — 30 Jul to 05 Aug 2026

Phase 1: Infrastructure (30 Jul - 01 Aug)  +  Phase 2: Dataset Validation (02 - 05 Aug)

## Week 1 Goal

Build the full synthetic degradation pipeline, YAML configs, dummy dataset, 37+ unit tests, dataset validation pipeline, experiment logger, and visual preview QC.

### Member 1 — ML Engineer (Week 1)

Phase 1 (30 Jul – 01 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Set up Git repo, virtual environment, CI skeleton (GitHub Actions) | CI runs on every push |
| 2 | Implement degradation.py — Gaussian noise, Poisson noise | Same seed = bit-identical output |
| 3 | Add Gaussian blur + motion blur to degradation.py | All degradation modes functional |
| 4 | Add SR downsampling x2, x4 to degradation.py | Downsampled outputs correct shape |
| 5 | Author degradation.yaml base config + 5 preset YAMLs with schema_version | All 6 configs load without error |

Phase 2 (02 – 05 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 6 | Tune noise + blur YAML ranges against wafer image samples | Configs updated and committed |
| 7 | Ensure all configs remain schema-versioned after tuning | Validation passes on all configs |
| 8 | Begin train.py stub (training loop skeleton — parallel, Day 4 of Phase 2) | train.py imports and runs without crash |

Unblocks: Member 3's tests, Member 2's dataset work, Member 4's preview tool

### Member 2 — Data / Validation Engineer (Week 1)

Phase 1 (30 Jul – 01 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Build SEMPairDataset in wafer_dataset.py (crop, augment, degrade, return tensors) | Returns valid tensor pairs for all presets |
| 2 | Build make_dummy_dataset.py → generates PNGs + manifest.json | Single command generates valid output |
| 3 | Run make_dummy_dataset.py and verify output | PNGs load, manifest schema valid |

Phase 2 (02 – 05 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Build validate_dataset.py (pixel stats, corrupt-file detection, duplicate check) | DoD checklist above met |
| 5 | Run on dummy dataset → produce validation_report.json | Report shows 0 errors |
| 6 | Implement ExperimentLogger in logger.py → writes experiment.csv with git_commit | DoD checklist above met |
| 7 | Verify logger appends a complete row with valid git hash | Manual spot-check + unit test |

Depends on: Member 1's degradation.py (preset configs needed for SEMPairDataset)

Unblocks: Member 3's week-2 training work, Member 4's preview tool

### Member 3 — Testing / QA Engineer (Week 1)

Phase 1 (30 Jul – 01 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Write 37 unit tests (noise, downsample, dataset, reproducibility) | pytest → 37 tests, 0 failures |
| 2 | Reproducibility test: same seed = bit-identical degradation output | Test passes |
| 3 | CI pipeline runs all tests on every push | CI shows green |

Phase 2 (02 – 05 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Add CI gate: exit code 1 on corrupt files or duplicates | CI fails correctly when injected |
| 5 | Write tests for validate_dataset.py (inject corrupt + duplicate, verify CI fails) | Tests pass |
| 6 | Write test for ExperimentLogger (row append + git_commit column populated) | Test passes |
| 7 | Keep running total at 0 failures | pytest green at end of every day |

Depends on: Member 1's degradation.py and Member 2's validate_dataset.py to write tests against

### Member 4 — Docs / Integration Lead (Week 1)

Phase 1 (30 Jul – 01 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Document YAML config schema (field meanings, allowed ranges) | Schema doc committed |
| 2 | Draft README.md quickstart (setup command, how to run tests) | New team member can onboard in under 5 min |
| 3 | Integration check — confirm all modules import together without error | No import errors |

Phase 2 (02 – 05 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Build preview_pairs.py → degradation_preview.png + *_meta.json | Visual grid generated |
| 5 | Run preview_pairs.py → visually review degradation_preview.png | Team sign-off on preview |
| 6 | Write docs/degradation_pipeline.md (all examples runnable) | Doc complete, all code examples run |
| 7 | Submit doc for team review → merge within 2-hour time-box | PR merged |

Depends on: Member 1's configs, Member 2's dataset tools existing to preview

# Week 2 — 06 Aug to 15 Aug 2026

Phase 3: Baseline Training (06-09 Aug)  +  Phase 4: SR x2 (10-12 Aug)  +  Phase 5: Submission Prep (13-15 Aug)

Roles rotate — every member switches to a new role.

| Member | Week 1 Role | Week 2 Role |
| --- | --- | --- |
| Member 1 | ML Engineer | Data / Validation |
| Member 2 | Data / Validation | Docs / Integration |
| Member 3 | Testing / QA | ML Engineer |
| Member 4 | Docs / Integration | Testing / QA |

### Member 1 — Data / Validation Engineer (Week 2)

Phase 3 (06 – 09 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Run training on denoise_light, denoise_medium, denoise_heavy presets | All 3 converge, no NaN/Inf |
| 2 | Compute PSNR + SSIM on held-out validation split for all 3 presets | Metrics logged per run |
| 3 | Log all runs to experiment.csv (config, git commit, epoch, loss, PSNR, SSIM) | CSV has 3 complete rows |

Phase 4 (10 – 12 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Run SR x2 training with sr_x2.yaml | Converges, checkpoint saved |
| 5 | Compute PSNR + SSIM for SR x2 on held-out test split | Metrics logged |
| 6 | Log SR x2 run to experiment.csv | CSV has 4 complete rows |
| 7 | Produce consolidated benchmark table (denoise x3 + SR x2) | Table complete, numbers match CSV |

Phase 5 (13 – 14 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 8 | Archive experiment bundle (configs, weights, CSV, docs) | Archive accessible |
| 9 | Verify experiment.csv has traceable run history with git hashes | Spot-check 3 runs trace to commits |

Depends on: Member 3's train.py fully working

Unblocks: Member 2's benchmark table, technical report, and demo video

### Member 2 — Docs / Integration Lead (Week 2)

Phase 3 (06 – 09 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Document baseline benchmark targets (PSNR range from literature) | Section committed to docs |
| 2 | Create before/after image gallery (min 6 samples x 3 presets = 18 images) | Gallery committed, visually reviewed |
| 3 | Review and merge all open Phase 2 PRs | No open PRs from Week 1 |

Phase 4 (10 – 12 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Run infer.py on unseen wafer images → inspect SR x2 outputs visually | No errors, outputs look correct |
| 5 | Write Round 1 limitations section (x4 deferred, LPIPS deferred, colour deferred) | Limitations doc committed |
| 6 | Begin writing technical report (methodology + results) | Draft complete |

Phase 5 (13 – 14 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 7 | Record demo video: raw → denoised → SR x2 (record by 14 Aug) | Video recorded and reviewed |
| 8 | Finalise and proofread technical report | Proofread by 1 other member, PDF ready |
| 9 | Complete submission checklist review | All boxes ticked |
| 10 | Merge all open feature branches to main | git log --oneline main shows clean history |

Depends on: Member 1's benchmark table + Member 3's infer.py working

Hard deadline: Demo video must be recorded by 14 August (1 day contingency)

### Member 3 — ML Engineer (Week 2)

Phase 3 (06 – 09 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Implement train.py — training loop, DataLoader with seed_worker, checkpoint saves | DoD checklist above fully met |
| 2 | Select denoising architecture: UNet or DnCNN | Decision documented in code comment |
| 3 | Configure L1 loss (+ optional perceptual loss) + Adam optimiser | Confirmed with Member 1 before training runs |
| 4 | Save best checkpoint per preset with config snapshot alongside | Checkpoints verified loadable |

Phase 4 (10 – 12 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 5 | Adapt train.py for SR task (SR-specific L1 + perceptual loss) | DoD checklist met for SR |
| 6 | Implement infer.py (single-image + batch mode) | DoD checklist above fully met |
| 7 | Run infer.py on unseen images, verify no errors | Zero errors on 5+ test images |

Phase 5 (13 – 14 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 8 | End-to-end smoke test on a clean environment (fresh clone → setup → full pipeline) | Pipeline runs in one setup command |
| 9 | Verify train.py accepts --config for all presets | Manual test of each preset |
| 10 | Verify infer.py runs on unseen images | Zero errors confirmed |

Unblocks: Member 1's training runs, Member 4's test writing, Member 2's demo video

### Member 4 — Testing / QA Engineer (Week 2)

Phase 3 (06 – 09 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 1 | Write unit tests for train.py (DataLoader seeding, checkpoint save/load, loss) | Tests pass, CI green |
| 2 | Expand test suite toward 50+ total tests | Running total visible in PR |
| 3 | Ensure CI passes on every PR with 0 failures | CI badge green |

Phase 4 (10 – 12 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 4 | Write unit tests for infer.py (single-image + batch mode) | Tests pass |
| 5 | Enforce lint gates (ruff/flake8) on all PRs via CI | CI blocks on lint failures |
| 6 | Reach 50+ unit tests, 100% pass rate | pytest output confirms 50+ tests |

Phase 5 (13 – 14 Aug)

| # | Task | Definition of Done |
| --- | --- | --- |
| 7 | Final CI audit — lint + test gates block failing PRs | Verified by trying a failing PR |
| 8 | Confirm CI green on main → get public CI run link for submission | Link ready |
| 9 | Verify Git repo is public or judge access granted | Access confirmed |

Depends on: Member 3's train.py + infer.py existing to write tests against

# 15 August — Final Integration Day (Feature Freeze)

No new features. No new code unless it is a bug fix.

| Time Block | Activity | Who |
| --- | --- | --- |
| Morning | Full pipeline smoke test (clean clone → setup → full run) | Member 3 leads |
| Morning | Fix any bugs found in smoke test (Critical = all hands) | All |
| Afternoon | Final pytest run — confirm 50+ tests, 0 failures | Member 4 |
| Afternoon | Proofread technical report one last time | Member 2 |
| Afternoon | Verify benchmark table numbers match experiment.csv | Member 1 |
| Evening | Final submission checklist walkthrough | All 4 together |
| Evening | git push origin main — final state | Member 3 or 4 |

# Round 1 Submission Checklist (16 Aug 2026)

| Item | Owner | Status |
| --- | --- | --- |
| Git repo public / judge access granted | Member 4 | Pending |
| README.md with quickstart (single setup command) | Member 2 | Pending |
| All model checkpoints accessible (link or archive) | Member 3 | Pending |
| Benchmark table (denoise x3 + SR x2) | Member 1 | Pending |
| Demo video attached or linked | Member 2 | Pending |
| Technical report attached (PDF or DOCX) | Member 2 | Pending |
| experiment.csv with traceable run history | Member 1 | Pending |
| pytest suite passing on CI (link to CI run) | Member 4 | Pending |

# Role Rotation

Every member experiences every role across the two-week hackathon: ML Engineer, Data/Validation, Testing/QA, and Docs/Integration.